## Risk
Risk | Probability | Impact | Importance | Response
ROS 2 connection loss during a competition task causes full control blackout | Medium | High | Very High | Auto-reconnect with retry counter. Disable all controls and show full-width warning on disconnect. E-STOP halts rover before link is confirmed lost.
High ROS 2 topic latency causes stale telemetry (coordinates, arm state) displayed as current. | Medium | High | Very High | Timestamp all incoming data. Mark values stale if topic silent >2 s. Never silently display outdated values.
Arm joint reaches hardware limit during operation, causing mechanical damage. | Medium | High | Very High | Joint limit warnings (Should Have) with colour gradient. Software joint limit enforcement in ROS 2 before command is sent. E-STOP always available.
Operator activates E-STOP unintentionally during autonomous navigation, disrupting run. | Medium | High | Very High | E-STOP requires deliberate press (not accidental brush). Add 0.5 s hold-to-confirm for E-STOP in Navigation view only, where accidental press risk is higher.
Operator collects wrong-color sample because camera feed does not accurately represent true colors. | Medium | High | Very High | White balance calibration available before task. Photo capture for visual comparison. Operator training on color calibration procedure.
ROS 2 topic names and message types not finalised by rover team, blocking GUI integration. | High | High | Very High | Resolve OQ-01 early. Define interface contract (topic list, message types) as first integration milestone. Use mock ROS 2 publisher for GUI development in parallel.
Robotic arm does not support Cartesian end-effector control (OQ-03), requiring rework of arm control UI. | High | High | Very High | Resolve OQ-03 early. Design arm control UI to support both joint-by-joint and Cartesian modes. Abstract control layer in code.
Insufficient testing time with real rover hardware before competition. | High | High | Very High | Test with mock ROS 2 nodes from day one. Schedule minimum two full hardware integration sessions before competition.
Camera feed lost or frozen mid-task, leaving operator without visual feedback. | Medium | Medium | High | Show 'No Signal' placeholder immediately on feed loss. Never silently display a frozen frame. Alert in persistent bar.
Poor color accuracy under outdoor lighting causes incorrect sample color identification in Science task. | High | Medium | High | White balance and brightness controls (Should Have). Default auto-white-balance on startup. Operator can manually calibrate before sampling.
Accidental switch to ARM mode while driving causes unexpected arm movement. | Medium | Medium | High | Require deliberate gamepad button hold (not tap) for mode switch. Large visual confirmation on every mode change. ARM movements disabled during DRIVE mode.
ImGui render loop blocks on ROS 2 I/O, causing UI freeze or frame rate drop below 30 FPS. | Medium | Medium | High | Run ROS 2 callbacks on a separate thread. GUI render loop never waits on network I/O. Spin executor decoupled from render loop.
Operator switches views mid-task and loses track of active operation (e.g. recording running in background). | Medium | Medium | High | Active-operation indicators persist across all views in the status bar (recording dot, arm mode badge). Confirmation prompt if switching views while recording.
Operator confuses DRIVE and ARM mode under pressure, sending drive commands while in ARM mode. | High | Medium | High | Drive/Arm mode badge is the most visually prominent element after E-STOP. Colour-codes entire persistent bar. Audio cue on mode switch if platform supports it.
Wireless interference at competition site causes intermittent ROS 2 signal drops. | High | Medium | High | Graceful degradation: brief drop (<500 ms) does not disable controls. Sustained drop shows warning. Last known safe state maintained until reconnection.
Should Have features not completed in time for competition, leaving the GUI incomplete. | Medium | Medium | High | Prioritise Must Have features first. Track Should Have as a separate milestone. Ensure Must Have features are stable 1 week before competition.
Gamepad disconnects during a critical operation (e.g. arm mid-movement). | Low | High | Medium | Detect gamepad disconnect immediately. Send zero-velocity command to rover and arm. Show warning and activate keyboard fallback automatically.
ROS 2 message type mismatch between GUI and rover software causes silent command failure. | Low | High | Medium | Define and agree all topic names and message types with rover team before integration. Validate at startup; log and alert on type mismatch.
Drill command sent while arm is not in correct position damages sample or hardware. | Low | High | Medium | Drill controls only active when arm is in a valid pre-drill pose (checked via joint state). Confirmation required before drill start.
Operator places sample in wrong container slot due to unclear container occupancy display. | Low | Medium | Medium | Container occupancy panel shows numbered slots with clear empty/occupied state. Active slot highlighted during arm placement operation.
Operator cannot locate a control quickly under competition time pressure. | Low | Medium | Medium | All primary controls reachable within 1–2 interactions. Keyboard shortcut help overlay (press '?'). Pre-competition familiarisation testing required.
Camera hardware or ROS 2 image driver does not deliver sufficient frame rate or color fidelity. | Low | Medium | Medium | Test camera pipeline early. Document minimum camera requirements. Have fallback resolution/encoding settings ready.
Camera decoding on main thread causes dropped frames and visible stuttering. | Medium | Low | Low | Decode camera frames on a dedicated worker thread. Double-buffer frame output to GUI.
Application crash during Science task recording corrupts or loses the entire video file. | Low | Low | Low | Write video incrementally to disk. Use container format (e.g. MKV) that is crash-recoverable. Flush after every keyframe.
Bright sunlight or glare on the operator screen makes GUI unreadable. | Medium | Low | Low | Dark theme with high-contrast text and colour-coded indicators. Minimum font sizes enforced. Consider screen brightness advisory in setup checklist.

## Scale
Very High
High
Medium
Low